## Slide 1
MDF1 AI Production System – From Data to Decision
From zero to current situation — updated project review
TRAINING + PREDICTION + GUI SERVICES
CURRENTLY SERVED: DENSITY + BENDING
NEXT: DB LOGGING + COCKPIT HARDENING
Raw dataset
3,128 × 1,165
KSoft source data
Clean usable rows
486
after validation + cleaning
Engineered features
26–28
pressure / temp / thickness
Served model R²
~0.69
density & bending RF bundles
GUI direction
Cockpit
prediction history + operations view
Reviewed source base: uploaded project deck, model summaries, training / repo notes, current GUIService direction, and April 2026 build status.
April 30, 2026 review update
MDF1 ML PROJECT
01

## Slide 2
Executive snapshot
What exists now, what changed in this update, and how the current position should be communicated.
MDF1 ML PROJECT
02
Business objective
Predict MDF1 quality targets from KSoft production signals so the organization can move from reactive lab inspection to earlier, data-driven quality decisions.
What is built now
Offline TrainingService, governed artifacts, FastAPI PredictionService, and first GUIService cockpit layer for human-facing prediction review.
Current proven status
Approved bundles load successfully; /health, /models, /predict and /predict-all patterns are established; GUI is becoming the operator-facing layer.
Current strongest story
• End-to-end ML system, not only notebooks
• Training and serving are separated
• RF remains strongest practical default for served density and bending
• Architecture now supports GUI + DB logging direction
Most important caveats
• Dataset is still small after cleaning
• Reporting needs one official reference metric view
• API packaging, monitoring and release hygiene are still open
• GUI/DB layer is prototype-to-hardening, not final production
Served density RF
R² 0.6905
labDensityAverage_rf_v1
Served bending RF
R² 0.6923
labBendingAvg_rf_v1
Best 5-target RF
R² 0.7578
labSurfaceSoundnessAvg
Current update
GUI + DB
cockpit and prediction logging path
Time range
Aug 2025 – Mar 2026
baseProductionDate

## Slide 3
From zero to now: project journey
The project matured through concrete engineering steps, not a single model-training event.
MDF1 ML PROJECT
03
1
1. Schema reality
check
Initial mismatch and missing columns exposed.
2
2. Clean MDF1
base
Raw KSoft data reduced to 486 usable rows.
3
3. Engineer process
signals
Pressure, temperature and thickness summaries added.
4
4. Stabilize
modeling
Split logic, feature filtering and artifact naming stabilized.
5
5. Systemize
serving
Training artifacts feed live REST prediction service.
Stakeholder narrative
Present the MDF1 work as a staged engineering journey: schema fixing → data governance → feature design → baseline benchmarking → artifact governance → live prediction + cockpit direction.

## Slide 4
Data foundation and preparation
The core signal base comes from KSoft production data and becomes smaller—but much more usable—after cleaning.
MDF1 ML PROJECT
04
Raw source
3,128 rows
1,165 columns from KSoft
After cleaning
486 rows
1,164 columns
Time coverage
Aug 2025 – Mar 2026
baseProductionDate
Engineered features
26 added
pressure / temp / thickness
Candidate model set
28 features
usable numeric features
Data reduction story
Raw KSoft extract — 3,128 rows / 1,165 cols
Validation + schema checks — required vs optional fields
Cleaning + high-missing removal — e.g., operFibresDensity dropped
Usable MDF1 training base — 486 rows
What this means analytically
• Data volume is not large, so split strategy and leakage control matter more than model complexity.
• Cleaning improves reliability of the modeling base.
• Several months of operations support time-based validation rather than pure random shuffling.
• Model quality comes from disciplined curation, not only algorithm choice.
TIME-BASED SPLIT
SMALL BUT GOVERNED DATASET
MANUFACTURING SIGNALS

## Slide 5
Feature engineering: turning press behavior into learnable signals
The most important improvement was converting raw plant readings into stable, interpretable process summaries.
MDF1 ML PROJECT
05
Pressure group
• L / C / R means and stds
• Global min / max / range
• Front / mid / end means
• Front-end difference
Temperature group
• Global mean and std
• Min / max / range
• Thermal state summarization
Thickness group
• Closed-thickness mean
• Std / min / max
• Range as board stability signal
Why these engineered features matter
They reduce noisy point-level readings into process-shape indicators: distribution across the press, thermal regime, thickness stability, and cross-zone balance.
The signal pattern already seen in results
Across targets, the most stable driver families are raw/thickness variables, aggregated press-pressure variables, and temperature / process-state variables. Example drivers include rawThickness, pressPressureGlobal_mean, pressPressureC_mean, thicknessClosed_mean, pressPressureMid_mean, and pressPressureFrontEnd_diff.
26 ENGINEERED FEATURES
DRIVER FAMILIES ARE CONSISTENT

## Slide 6
Modeling evolution and lessons learned
The story is stronger when it shows how unstable experiments became a governed baseline.
MDF1 ML PROJECT
06
What went wrong early
• Prototype runs selected unusable fields such as abs24h / vkstockProxy variables.
• Warnings appeared for features with no observed values.
• Feature-importance export once failed because arrays did not match.
• XGBoost once saw a training / feature-name mismatch.
What changed in the mature pipeline
• Feature filters exclude nonnumeric, all-null, target, leakage-prone and irrelevant fields.
• Time-based splitting and repeatable artifact naming were standardized.
• Training saves governed bundles and the serving layer reads the exact saved feature order.
Key lesson for the presentation
Show that the team learned to trust the system only after data filters, split logic and artifact governance were stabilized. This makes the final served performance more credible than flashy but fragile early numbers.
Reporting guidance
Use three result layers: 1) early prototype findings for learning only, 2) five-target baseline comparison, 3) current served bundles and API-verified system state.
EARLY RUNS ≠ CURRENT STATE
GOVERNED BASELINE

## Slide 7
Project-wide baseline comparison: five quality targets
The broader MDF1 view shows multiple targets are learnable, but not equally ready for rollout.
MDF1 ML PROJECT
07
Five-target baseline performance
0.758
Surface
Soundness
0.742
Density
0.727
Bending
0.708
Tensile
0.693
E-Modul
R²
Interpretation
• Best current five-target baseline: labSurfaceSoundnessAvg (RF R² = 0.7578).
• Strong and consistent performers: labDensityAverage and labBendingAvg.
• labTensileAvg is still respectable.
• labEModulAvg is weakest and should be refined later.
Recommended deployment order
Phase 1 Surface soundness + Density
Phase 2 Bending + Tensile
Phase 3 E-Modul after more refinement
Stakeholder message
MDF1 is not a one-model story. It is a portfolio of learnable quality targets, with density and surface soundness leading the deployment conversation.

## Slide 8
Current served focus: density and bending
These are the two targets already reflected in the reviewed PredictionService state and active artifact bundles.
MDF1 ML PROJECT
08
Current served-target algorithm comparison
RF
XGB
LGBM
RF
XGB
LGBM
Density
Bending
labDensityAverage
R² 0.6905
labDensityAverage_rf_v1
labBendingAvg
R² 0.6923
labBendingAvg_rf_v1
Density signal story
Top drivers repeatedly point to board geometry plus aggregated press-pressure behavior: rawThickness, pressPressureGlobal_mean, pressPressureC_mean.
Bending signal story
Bending performance is strongly linked to thickness stability and mid-press conditions: rawThickness, thicknessClosed_mean, pressPressureMid_mean.
Decision point
RF still edges out XGB and LGBM for both currently served targets, so it remains the strongest practical default for live bundles reviewed here.

## Slide 9
Updated system architecture: three services plus governed artifacts
The latest update adds the human-facing GUI layer and prepares the system for prediction logging.
MDF1 ML PROJECT
09
KSoft / MDF1 data
raw production signals + lab targets
TrainingService
validation, cleaning, engineered features, time split, model training
Artifact bundles
model.joblib, features.json, metrics.json, metadata.json
PredictionService
loads approved RF bundles and serves /predict + /predict-all
GUIService
operator cockpit, manual prediction, history view
PostgreSQL log
prediction traceability, status, model, source
Most important architecture point
Inference is governed by the exact saved feature list. The GUI should never send arbitrary column order; it should call PredictionService with a controlled feature payload and store the result for later comparison with real lab values.
OFFLINE LEARNING
ONLINE SERVING
HUMAN DECISION LAYER

## Slide 10
GUIService update: from API page to production cockpit
The GUI should be positioned as the human decision layer—not just a front-end form.
MDF1 ML PROJECT
10
What the GUI does now / next
• Calls PredictionService for target predictions.
• Displays prediction output, model name, algorithm and missing features.
• Shows history rows with time, order, board, target, prediction, model and status.
• Uses color classes to highlight normal / attention / risk states.
Cockpit concept
Prediction request
Risk / attention status
Prediction history
Order
Board
Target
Prediction
Status
PO-105
B-231
Density
758.4
OK
PO-105
B-232
Bending
28.7
ATTENTION
PO-106
B-240
Density
771.2
HIGH
Why yellow appears
Yellow should be treated as an attention / warning color. It means the prediction crossed a configured threshold or needs operator review; it should not be interpreted as a system failure.
Recommended GUI wording
Use neutral production language: Normal, Attention, Risk, Missing input, Model unavailable. Avoid confusing colors unless the legend is visible on the page.
OPERATOR-FACING
TRACEABLE OUTPUT
CLEAR STATUS LEGEND

## Slide 11
Prediction logging: the production traceability layer
PostgreSQL logging turns predictions from one-off API results into auditable production records.
MDF1 ML PROJECT
11
Prediction request
features, target, source
PredictionService response
prediction, model, algorithm, missing inputs
prediction_log table
created_at, order, board, target, prediction, model, status
Monitoring view
predicted vs actual, drift, trust
Why this matters
• Production AI needs traceability: which model predicted what, when, and from which input source.
• Logs enable comparison against later lab results.
• Logs enable model drift monitoring and retraining triggers.
• Logs support management reporting and operator trust building.
Minimum useful fields
id, created_at, production_order, board_id, target_name, prediction_value, model_name, algorithm_name, source, status, missing_features_json, request_payload_json
Recommended next implementation
Keep the GUI simple: first read from prediction_log and render the last predictions. Later add filtering by target, order, time range, status and model version.

## Slide 12
Current maturity: proven value vs. production hardening
This framing avoids overselling while still showing clear progress.
MDF1 ML PROJECT
12
Already proven
• Repeatable MDF1 data preparation and engineered-feature generation exist.
• Five quality targets have been benchmarked with consistent RF baselines.
• Artifact bundles are structured and readable by a separate PredictionService.
• /predict and /predict-all patterns support live predictions.
• Density and bending have named RF bundles in the served state.
• GUIService direction now makes the system visible to operators.
Still open before production confidence
• Unify one official metric view across deck, comparison sheets and served bundles.
• Harden API behavior: default model handling, error messages, packaging / Docker.
• Improve repo / release hygiene around unstaged changes and artifact promotion flow.
• Add prediction logging, monitoring and drift control.
• Collect more data to strengthen generalization, especially lower-ranked targets.
• Stabilize GUI configuration, status legend and DB-backed history.
PROVEN VALUE
NOT YET FULL PRODUCTION
Recommended positioning
“Operational ML system with verified inference and a cockpit/logging path — not yet a fully hardened production platform.”

## Slide 13
Recommended roadmap from current state
A pragmatic rollout path connects the technical status to operations and management value.
MDF1 ML PROJECT
13
Phase 1 — validate in operations
• Freeze official metric reference.
• Use density + surface soundness as proof cases.
• Compare prediction vs actual lab result.
• Review thresholds with MDF1 experts.
Phase 2 — harden the cockpit
• Connect GUI to DB-backed prediction history.
• Standardize status colors and legends.
• Add filters by target, order, board and date.
• Improve error handling and missing-feature visibility.
Phase 3 — industrialize
• Package services and define release flow.
• Add monitoring: drift, stability, latency.
• Set retraining cadence and model promotion rules.
• Prepare MES / Lira integration path.
Recommended closing message
MDF1 ML has already crossed the most important threshold: it is no longer just a modeling exercise. It is now an end-to-end ML system with credible baselines, governed artifacts, verified inference, and a clear path to a production cockpit.

## Slide 14
Decision asks for the next review
The next management conversation should convert technical progress into a controlled rollout plan.
MDF1 ML PROJECT
14
1. Agree official metric reference
Select one authoritative result table for reporting: served bundles vs broader five-target baseline. This prevents inconsistent R² numbers across materials.
2. Approve pilot scope
Start with density and surface soundness / bending depending on business priority, then track prediction vs actual lab values.
3. Approve logging + cockpit hardening
Make PostgreSQL prediction_log and GUI history table the next delivery focus before MES automation.
Practical next sprint
• Finalize status-threshold rules and color legend.
• Persist every prediction to PostgreSQL.
• Add filters and clearer history view in GUIService.
• Prepare a demo script: input → prediction → history → follow-up actual.
Strategic message
This is a production-safe learning system: start with decision support, log every prediction, compare with real outcomes, and only then move toward automated MES actions.
CONTROLLED PILOT
TRACEABILITY FIRST
MES AUTOMATION LATER